## Sheet1
Sprint 3 - Android App User Stories v.03 (Unity) | To Do | Doing | Done | Graphics Team: | Sound Engineer: | Unity Team: | Webapp:
A player will be authenticated by their device’s via default Google Play Account. | Unity Team | Unity Team | Unity Team | John | Joe | Loi | Donovan
A player is able to create a new game. | Unity Team | Unity Team | Unity Team | Marcel |  | Austin | Joe
A player is able to view credits. | Unity Team | Unity Team | Unity Team |  |  | Olivia
A player’s score will be saved to Google Play Services. | Unity Team | Unity Team | Unity Team
A player is able to navigate between all Dogeons and Dragons app activities. | Unity Team | Unity Team | Unity Team | Sprint 3 - Android App User Stories v.03 (Sound) | To Do | Doing | Done
A player will be able to collect units. | Unity Team | Unity Team |  | A player will hear a musical theme while accessing the main menu. | Sound Team | Sound Team | Joe
A player will be able to collect chewables. | Unity Team | Unity Team |  | A player will hear a sound when tapping a menu option. | Sound Team | Sound Team | Joe
A player will be able to select units to use in battle. | Unity Team | Unity Team | Unity Team | A player will hear a different musical theme during battle. | Sound Team | Sound Team | Joe
A player will be able to attack with their selected unit during battle. | Unity Team | Unity Team | Unity Team | A player will hear a victory theme when they complete a level. | Sound Team | Sound Team | Joe
A player will be able to take damage with their selected unit during battle. | Unity Team | Unity Team | Unity Team | A player will hear a defeat theme when they lose against an enemy. | Sound Team | Sound Team | Joe
A player will be able to select chewables to use during a level. | Unity Team | Unity Team |  | A player will hear a unit make a sound when attacking in battle. | Sound Team | Sound Team | Joe
A player will be rewarded after a victory. | Unity Team | Unity Team |  | A player will hear a unit make a sound when hit in battle. | Sound Team | Sound Team | Joe
A player will progress to harder levels after each level victory. | Unity Team | Unity Team |  | A player will hear a unit make a sound when killed in battle. | Sound Team | Sound Team | Joe
A player can restart a level if they lose. | Unity Team | Unity Team |  | A player will heal a unit make a sound when healed in battle. | Sound Team | Sound Team | Joe
A player will be able to view completed levels. | Unity Team | Unity Team |  | A player will hear a unit make a sound when eating power ups. | Sound Team | Sound Team | Joe
A player will be able to view incomplete levels. | Unity Team | Unity Team |  | A player will hear a unit make a sound when selected to use. | Sound Team | Sound Team | Joe
A player will be able to collect currency after a level victory. | Unity Team | Unity Team
A player will be able to summon new units. | Unity Team | Unity Team |  | Sprint 3 - Android App User Stories v.03 (Graphics) | To Do | Doing | Done
A player can return to the point in the game they were at, after exiting the game. | Unity Team | Unity Team |  | A player will fight enemies visually represented as 2d sprites. | Graphics Team | Graphics Team
A player is able to download Dogeons and Dragons from Google Play store. | Unity Team | Unity Team |  | A player will have chewables visually represented as 2d sprites. | Graphics Team | Graphics Team
|  |  |  | A player will have units visually represented as 2d sprites. | Graphics Team | Graphics Team
|  |  |  | A player will see a unit animated when attacking in battle. | Graphics Team | Graphics Team
|  |  |  | A player will see a unit animated when being hit in battle. | Graphics Team | Graphics Team
|  |  |  | A player will see a unit is hurt in battle. | Graphics Team | Graphics Team
|  |  |  | A player see a unit is healthy in battle. | Graphics Team | Graphics Team
|  |  |  | A player will experience custom backgrounds on each screen of the application. | Graphics Team | Graphics Team
|  |  |  | A player will use custom UI buttons. | Graphics Team | Graphics Team
Sprint 3 - Webapp and Database User Stories v.03 (Web) | To Do | Doing | Done
A player will be able to access a webapp about the game. | Web Team | Web Team | Web Team
A player will be able to view all available units in the game on the webapp. | Web Team | Web Team | Web Team
A player will be able to view all available chewables in the game on the webapp. | Web Team | Web Team
A player will be able to view all tutorials about the game on the webapp. | Web Team | Web Team |  | Sprint 3 - Webapp and Database User Stories v.03 (Graphics) | To Do | Doing | Done
A player will be able to view all stories about the game on the webapp. | Web Team | Web Team |  | A player will exeperience custom graphics on the webapp. | Graphics Team | Graphics Team
An admin will be authenticated on the webapp. | Web Team | Web Team | Web Team
An admin will be able to view, add, delete or update all available units in the game on the webapp. | Web Team | Web Team | Web Team
An admin will be able to view, add, delete or update all available chewables in the game on the webapp. | Web Team | Web Team
An admin will be able to view, add, delete or update all available tutorials about the game on the webapp. | Web Team | Web Team
\